## Agent Overview
🤖 AI Inbox Management — Multi-Agent System Overview
Agent ID | Agent Name | Epic Mapped | Role / Purpose | LLM Required | Framework | Trigger | Output | Status
AG-00 | Orchestrator Agent | Cross-Epic | Master controller — dispatches tasks to all agents, manages state machine, handles errors and retries | Yes (Claude Sonnet) | LangGraph StateGraph | New email event / webhook | Task dispatch to sub-agents + state update | Core
AG-01 | Intake Agent | E1 — Inbox Monitoring & Intake | Polls all email sources, extracts metadata (sender, subject, body, attachments), sends auto-ACK, stores attachments | No (rule-based) | LangGraph Node + Python | Scheduled poll / webhook push | Structured email object → Orchestrator | Core
AG-02 | Classification Agent | E2 — Categorization & Tagging | Classifies email type, assigns priority (High/Med/Low), detects sentiment, computes confidence score | Yes (Claude Sonnet) | LangGraph Node + Claude API | Email object from AG-01 | Classification tags + sentiment score → State Store | Core
AG-03 | Routing Agent | E3 — Triage & Routing | Routes email to correct team/SME/queue using rule-based logic + AI fallback, logs routing decision | Yes (Claude — fallback) | LangGraph Node + Rules Engine | Classification output from AG-02 | Routing decision + ticket assignment | Core
AG-04 | Response Agent | E4 — Response Management | Generates AI-drafted reply, checks tone, masks PII/GDPR fields, human-in-loop before send | Yes (Claude Sonnet) | LangGraph Node + Claude API | Routing decision from AG-03 | Draft email → Human review → Send | Core
AG-05 | SLA Agent | E5 — SLA & Follow-up Management | Tracks SLA deadline per email, fires alerts at 80% elapsed, auto-escalates at 100% breach, feeds aging dashboard | No (cron-based) | LangGraph Node + APScheduler | Email intake event (background) | Slack / email alerts + escalation trigger | Core
AG-06 | Audit & Compliance Agent | E6 — Documentation & Audit Trail | Logs every agent action, email, response, routing decision; archives attachments; enforces HIPAA/GDPR; exports audit trail | No (event-driven) | LangGraph Node + Async Logger | Every agent state change | Audit log records in DB + CRM | Core
AG-07 | Analytics Agent | E7 — Analytics & Continuous Improvement | Aggregates KPIs, mines repetitive query patterns, generates weekly insight report, tracks automation % and cost/email | Yes (Claude Sonnet) | LangGraph Node + Claude API | Scheduled (daily/weekly cron) | KPI dashboard data + weekly report | Core

## Agent Design Details
🔬 Agent Design Details — Inputs, Outputs, Tools, Prompts & Error Handling
Agent | Input Schema | Output Schema | MCP Tools Used | LLM Prompt Strategy | State Variables | Error Handling | Human-in-Loop? | Retry Policy
Orchestrator AG-00 | email_event: {id, source, timestamp} | task_dispatch: {agent_id, payload, priority} | postgres-mcp, slack-mcp | No direct LLM — uses deterministic routing graph. Claude used only for ambiguous state resolution. | email_id, current_step, agent_statuses, retry_count, global_sla_deadline | On agent failure: retry 3x → fallback queue → Slack alert to Team Lead | No — fully automated | Exponential backoff (1s, 2s, 4s). After 3 failures → dead-letter queue.
Intake Agent AG-01 | email_source_event: {source_type, raw_email_id} | email_object: {id, sender, subject, body, attachments[], timestamp, source} | gmail-mcp, outlook-mcp, zendesk-mcp, freshdesk-mcp, filesystem-mcp | No LLM. Rule-based extraction using email parsing libraries (imaplib / Graph API). | raw_email, parsed_email, attachment_paths, ack_sent | Connection timeout → retry with backoff. Parse error → log raw + flag for manual review. | No | Retry 3x on connection error. On persistent failure, alert Ops via Slack.
Classification Agent AG-02 | email_object (from AG-01) | classification: {type, priority, sla_bucket, sentiment, confidence_score, escalation_flag} | anthropic-claude-mcp, freshdesk-mcp, postgres-mcp | Structured output prompt: 'Classify this email. Return ONLY JSON: {type, priority, sla_bucket, sentiment, confidence}'. System prompt includes type taxonomy and priority rules. | email_text, classification_result, sentiment_score, confidence, low_confidence_flag | confidence < 0.7 → flag for human review. LLM timeout → fallback to keyword-based classifier. | Yes — if confidence < 0.7, route to human tagger | LLM call retry 2x. On failure, use keyword fallback classifier.
Routing Agent AG-03 | classification object (from AG-02) | routing_decision: {team, assignee, queue_id, routing_reason, timestamp} | servicenow-mcp, jira-mcp, freshdesk-mcp, postgres-mcp | Primary: Rule-based routing matrix (billing→Finance, IT issue→IT Support, etc.). Fallback: Claude prompt 'Given this email type and priority, which team should handle it? Choose from: [list]' | classification, routing_matrix, routing_decision, assignment_id | No matching rule → Claude fallback. Claude uncertain → escalate to Team Lead manually. | Yes — Team Lead can override routing via dashboard | Rule engine: no retry (deterministic). Claude fallback: retry 2x.
Response Agent AG-04 | routing_decision + email_object + customer_history (from CRM) | draft_response: {subject, body, tone_score, pii_detected, compliance_ok, requires_review} | anthropic-claude-mcp, gmail-mcp, outlook-mcp, crm-mcp, postgres-mcp | System prompt: 'You are a professional customer service agent. Draft a reply that is: accurate, empathetic, compliant (no PII, no informal language). Use customer name. Reference case ID.' + compliance guardrail pass. | email_thread, customer_context, draft, tone_score, pii_scan_result, analyst_edits | Tone score < threshold → regenerate. PII detected → mask + block send + alert compliance. | Yes — all drafts go to analyst for review before send. PII-flagged always blocked. | Draft generation: retry 2x. PII block is hard stop — no retry, manual resolution required.
SLA Agent AG-05 | email intake event: {email_id, sla_deadline, priority} | sla_status: {email_id, elapsed_pct, status, alert_sent, escalation_triggered} | postgres-mcp, slack-mcp, gmail-mcp | No LLM. Pure time-based logic: cron every 5 min → query all open emails → compute elapsed % → fire alerts. | sla_deadline, elapsed_time, alert_80_sent, escalated, current_assignee | DB connection failure → retry 3x → log error. Slack failure → fallback to email alert. | No — fully automated | DB retry 3x with 1s backoff. Alert deduplication: don't resend same alert within 30 min.
Audit Agent AG-06 | Every agent state change event: {event_type, agent_id, email_id, payload, timestamp} | audit_record: {event_id, email_id, action, agent, timestamp, before_state, after_state} | postgres-mcp, salesforce-mcp, hubspot-mcp, filesystem-mcp | No LLM. Event-driven async logger. Write-only, append-only DB pattern for tamper-proof trail. | event_queue, write_buffer, last_flush_time | Write failure → buffer locally → retry flush. Never drop an audit event. | No | Infinite retry with exponential backoff for audit writes — data must not be lost.
Analytics Agent AG-07 | postgres DB: aggregated email + classification + routing + SLA data | kpi_report: {volume, frt, sla_pct, fcr, sentiment_trend, automation_pct, cost_per_email} + weekly_insight_text | postgres-mcp, google-sheets-mcp, slack-mcp, anthropic-claude-mcp | Aggregation: SQL via postgres-mcp. Insight generation: Claude prompt 'Given these KPI trends, identify top 3 improvement opportunities and automation candidates. Be specific and data-driven.' | kpi_snapshot, trend_data, insight_text, report_timestamp | DB query timeout → retry 3x. Claude insight failure → skip insight, still publish KPI numbers. | No — fully automated | Scheduled job. On failure, notify Ops and skip cycle (don't block).

## LangGraph State Flow
🔄 LangGraph State Machine — Email Processing Flow
Step # | Node (Agent) | State Input | Action Performed | State Output | Condition / Branch | Next Node | Parallel?
1 | START | email_event trigger | Validate event payload, initialize state object | state = {email_id, status: 'new'} | Always proceed | AG-01 Intake | No
2 | AG-01 Intake | state.email_id, source_config | Fetch email from source, parse metadata, download attachments, send ACK | state.email_object, state.attachments, state.ack_sent | Parse success → continue Parse failure → dead-letter queue | AG-02 Classification | No
3 | AG-02 Classification + Sentiment (parallel) | state.email_object | Classify type/priority/SLA bucket; detect sentiment; compute confidence | state.classification, state.sentiment, state.confidence | confidence ≥ 0.7 → continue auto confidence < 0.7 → human tagger negative sentiment → escalation flag | AG-03 Routing (+ AG-05 SLA parallel) | Yes — classification + SLA start in parallel
4 | AG-05 SLA (parallel start) | state.email_id, state.classification.sla_bucket | Record SLA deadline, start background timer, schedule alert checks every 5 min | state.sla_deadline, state.sla_timer_started | Runs continuously in background until email closed | Background (continuous) | Yes — parallel with routing
5 | AG-03 Routing | state.classification | Apply routing rules matrix; assign to team/queue; log routing decision | state.routing_decision, state.assigned_team | Rule match → assign directly No rule match → Claude fallback Fallback fails → Team Lead queue | AG-04 Response | No
6 | AG-04 Response | state.email_object, state.routing_decision, customer_history | Generate AI draft; run tone check; scan for PII; route to human analyst for approval | state.draft_response, state.pii_detected, state.human_approved | PII detected → block + audit Tone fail → regenerate Human approved → send Human rejected → re-draft | AG-06 Audit (async) | No
7 | AG-06 Audit (async) | Every state change event | Log action, agent, timestamp, before/after state; archive attachments; check compliance | audit_records written to DB + CRM | Always runs async in background Compliance violation → alert compliance officer | Continuous (background) | Yes — always parallel
8 | AG-06 → CLOSE | state.human_approved = True, email sent | Mark email as closed; update SLA timer; write closure to audit log; update CRM | state.status = 'closed', state.closed_at | All conditions met → close Not met → remain open | END / AG-07 Analytics feed | No
9 | AG-07 Analytics (scheduled) | Aggregated DB data | Compute KPIs; generate insight; publish to dashboard; post weekly Slack report | kpi_dashboard updated, weekly_report generated | Daily KPI update Weekly full report | END | No

## MCP Tool Registry
🔌 MCP Tool Registry — Configuration & Agent Usage
MCP Tool ID | Tool Name | Category | Used By Agents | Auth Method | Key Config | Rate Limit / Notes | Fallback Strategy
MCP-01 | gmail-mcp | Email | AG-01, AG-04 | OAuth 2.0 (Google) | scopes: gmail.readonly + gmail.send | 500 req/day (free tier). Use batch for bulk. | Fallback to SMTP if MCP unavailable
MCP-02 | outlook-mcp | Email | AG-01, AG-04 | OAuth 2.0 (Microsoft Graph) | tenant_id, client_id, client_secret | 2000 req/10min Graph API limit | Fallback to IMAP/SMTP
MCP-03 | zendesk-mcp | Ticketing | AG-01 | API Token (Basic Auth) | subdomain, email, api_token | 700 req/min (Enterprise) | Queue + retry on 429
MCP-04 | freshdesk-mcp | Ticketing | AG-01, AG-02, AG-03 | API Key | api_key, domain | 80 req/min (Growth plan) | Exponential backoff on rate limit
MCP-05 | servicenow-mcp | ITSM | AG-03 | OAuth 2.0 | instance_url, client_id, client_secret | Varies by instance tier | Fallback to REST API direct call
MCP-06 | jira-mcp | Project Mgmt | AG-03 | API Token (Atlassian) | site_url, email, api_token | 300 req/min (Cloud) | Queue writes, retry on failure
MCP-07 | anthropic-claude-mcp | LLM | AG-02, AG-04, AG-07 | Anthropic API Key | model: claude-sonnet-4-20250514, max_tokens: 1000 | Tier-based RPM/TPM limits. Use streaming for long drafts. | Fallback to keyword classifier (AG-02) or template response (AG-04)
MCP-08 | postgres-mcp | Database | AG-00, AG-02, AG-03, AG-05, AG-06, AG-07 | DB Connection String | host, port, dbname, user, password, ssl=require | Connection pool: max 20. Query timeout: 10s. | Read replica for analytics. Write retries on deadlock.
MCP-09 | slack-mcp | Notifications | AG-02, AG-05, AG-07 | Bot Token (xoxb-) | channel IDs per alert type, signing_secret | Slack: 1 msg/sec per channel | Fallback to email alert if Slack unavailable
MCP-10 | salesforce-mcp | CRM | AG-04, AG-06 | OAuth 2.0 (Connected App) | client_id, client_secret, instance_url | API calls: 100,000/24hr (Enterprise) | Fallback to hubspot-mcp
MCP-11 | hubspot-mcp | CRM | AG-04, AG-06 | Private App Token | access_token, portal_id | 150 req/10sec | Fallback to direct DB write
MCP-12 | filesystem-mcp | Storage | AG-01, AG-06 | Service Account / IAM Role | base_path or S3 bucket config | No hard limit. File size max 25MB. | Local disk fallback if cloud unavailable
MCP-13 | google-sheets-mcp | Analytics Export | AG-07 | Service Account (JSON key) | spreadsheet_id, sheet_name | 300 req/min (Sheets API v4) | Export to CSV as fallback

## Implementation Roadmap
🗺️ Implementation Roadmap — Phase-wise Build Plan
Phase | Sprint | Agents to Build | Key Deliverables | MCP Tools to Connect | Dependencies | Success Criteria | Duration
Phase 1 Foundation | Sprint 1-2 | AG-01 Intake Agent | • Email polling from Gmail + Outlook • Auto-ACK sending • Attachment storage • Basic email object schema | gmail-mcp, outlook-mcp, filesystem-mcp | Email credentials, OAuth setup, DB schema | 100% emails ingested; ACK sent within 5 min; 0 missed emails in 24hr | 2 weeks
Phase 1 Foundation | Sprint 3 | AG-06 Audit Agent (basic) | • Append-only audit log DB • Log every intake event • Basic compliance checks | postgres-mcp, filesystem-mcp | PostgreSQL instance, schema design | 100% events logged; audit log queryable by email_id | 1 week
Phase 2 Intelligence | Sprint 4-5 | AG-02 Classification Agent | • Claude-powered classification • Sentiment detection • Confidence scoring • Human review queue for low-confidence | anthropic-claude-mcp, freshdesk-mcp, postgres-mcp | Claude API key, classification taxonomy, AG-01 complete | >90% accuracy; confidence score on every email; low-confidence flagged | 2 weeks
Phase 2 Intelligence | Sprint 6 | AG-03 Routing Agent | • Routing rules matrix • Ticket assignment to teams • Routing audit log • Manual override in dashboard | servicenow-mcp, jira-mcp, postgres-mcp | AG-02 complete, routing matrix defined by client | 95%+ routing accuracy; every decision logged with reason | 1 week
Phase 3 Response | Sprint 7-8 | AG-04 Response Agent | • AI draft generation • Tone checking • PII/GDPR masking • Human-in-loop approval UI • Send via email MCP | anthropic-claude-mcp, gmail-mcp, crm-mcp, postgres-mcp | AG-03 complete, CRM access, compliance rules documented | Draft in <5 sec; PII 100% blocked; analyst approval flow working | 2 weeks
Phase 4 Operations | Sprint 9 | AG-05 SLA Agent | • SLA timer per email • 80%/100% threshold alerts • Slack + email notifications • Aging dashboard data feed | postgres-mcp, slack-mcp, gmail-mcp | Slack workspace connected, SLA rules per priority defined | Alerts fire on time; 0 breached SLAs without escalation triggered | 1 week
Phase 4 Operations | Sprint 10 | AG-06 Audit Agent (full) | • Full compliance enforcement • CRM sync • Attachment archival • Export for audit reviews | postgres-mcp, salesforce-mcp, filesystem-mcp | CRM credentials, compliance rulebook | 100% audit completeness; export to PDF/Excel working | 1 week
Phase 5 Analytics | Sprint 11-12 | AG-07 Analytics Agent + AG-00 Orchestrator polish | • KPI dashboard real-time feed • Weekly AI insight report • Google Sheets export • Full orchestrator hardening, retries, dead-letter queue | postgres-mcp, google-sheets-mcp, slack-mcp, anthropic-claude-mcp | All agents complete, baseline KPI data available | Dashboard live; weekly report auto-posts to Slack; orchestrator handles all failure scenarios | 2 weeks

## Prompt Library
💬 LLM Prompt Library — Agent Prompt Templates
Prompt ID | Agent | Prompt Type | System Prompt | User Prompt Template | Expected Output Format
PROMPT-01 | AG-02 Classification | Email Classification | You are an expert email classifier for a business inbox management system. Classify emails accurately based on content, tone, and context. Always return valid JSON only — no explanation, no markdown. | Classify the following email: FROM: {{sender}} SUBJECT: {{subject}} BODY: {{body}} Return JSON: {"type": "<billing¦hr¦it¦complaint¦query¦escalation¦other>", "priority": "<high¦medium¦low>", "sla_bucket": "<4h¦8h¦24h¦48h>", "confidence": <0.0-1.0>} | {"type": "billing", "priority": "high", "sla_bucket": "4h", "confidence": 0.94}
PROMPT-02 | AG-02 Classification | Sentiment Detection | You are a sentiment analysis expert. Analyze the emotional tone of business emails. Return valid JSON only. | Analyze the sentiment of this email: SUBJECT: {{subject}} BODY: {{body}} Return JSON: {"sentiment": "<positive¦neutral¦negative¦angry>", "score": <-1.0 to 1.0>, "escalation_flag": <true¦false>, "key_phrases": ["...", "..."]} | {"sentiment": "negative", "score": -0.72, "escalation_flag": true, "key_phrases": ["unacceptable", "immediately"]}
PROMPT-03 | AG-03 Routing | Routing Fallback | You are a routing expert for a business inbox system. Route emails to the correct team. Available teams: Finance Ops, IT Support, HR Ops, Customer Service, Legal & Compliance, General Ops. Return JSON only. | Route this email: Type: {{type}} Priority: {{priority}} Subject: {{subject}} Summary: {{body_summary}} Return JSON: {"team": "<team_name>", "reason": "<one sentence reason>", "confidence": <0.0-1.0>} | {"team": "Finance Ops", "reason": "Email contains billing dispute related to invoice #1234", "confidence": 0.91}
PROMPT-04 | AG-04 Response | Draft Response Generation | You are a professional customer service agent. Write accurate, empathetic, and compliant email responses. Rules: (1) Use customer's name. (2) Reference case ID. (3) No PII in body. (4) Professional tone — no slang. (5) End with next steps. Return the email body only, no subject line. | Write a response email: Customer Name: {{customer_name}} Case ID: {{case_id}} Original Query: {{email_body}} Resolution: {{resolution_notes}} Team: {{assigned_team}} Write the response body only: | Dear {{customer_name}}, Thank you for reaching out. Regarding your case (Ref: {{case_id}})... [professional body] Next steps: ... Best regards, [Team Name]
PROMPT-05 | AG-04 Response | Compliance / PII Scan | You are a data privacy compliance checker. Detect any PII or sensitive data in outbound email text. Return JSON only. PII includes: SSN, credit card numbers, bank account numbers, medical record IDs, DOB, full address, passwords. | Scan this email for PII or compliance violations: {{email_draft}} Return JSON: {"pii_detected": <true¦false>, "violations": [{"type": "<pii_type>", "snippet": "<redacted_preview>"}], "safe_to_send": <true¦false>} | {"pii_detected": false, "violations": [], "safe_to_send": true}
PROMPT-06 | AG-07 Analytics | Weekly Insight Report | You are a business operations analyst. Analyze inbox management KPI data and provide actionable insights. Be specific, reference the numbers, and prioritize top 3 opportunities. Return structured text. | Analyze this week's inbox KPI data and provide insights: KPIs: {{kpi_json}} Previous week: {{prev_kpi_json}} Provide: (1) Top 3 performance highlights, (2) Top 3 areas needing improvement, (3) Top 3 automation opportunities, (4) One recommended action for next week. | 1. HIGHLIGHTS: SLA compliance improved from 88% to 94%... 2. AREAS TO IMPROVE: AHT increased by 12%... 3. AUTOMATION OPPORTUNITIES: 34% of emails are billing status queries — ideal for auto-response... 4. RECOMMENDED ACTION: ...