## Product Backlog
AI-Powered Inbox Management System — Product Backlog
Epic ID | Epic Name | User Journey ID | User Journey / Story | Who (Role) | Features | Acceptance Criteria | Approach | MCP Tools Used | Priority
E1 | Inbox Monitoring & Intake | E1-UJ1 | Email Ingestion & Auto-Acknowledgement | Inbox Analyst (L1) | • Auto-connect to Outlook/Gmail/Zendesk • Real-time email ingestion via OAuth/webhooks • Auto-reply with case reference number • Urgency detection from subject/body • Attachment capture & storage | ✅ Email ingested within 30 seconds ✅ Auto-ACK sent within 5 minutes ✅ No email missed in 24hr window ✅ Attachments captured and stored ✅ Case reference number in every reply | Connect via OAuth → Poll/webhook for new mail → Extract metadata → Trigger auto-reply → Store attachments in filesystem | gmail-mcp, outlook-mcp, zendesk-mcp, filesystem-mcp | High
E2 | Categorization & Tagging | E2-UJ1 | AI-Based Email Classification | AI/Automation Analyst, Inbox Analyst | • NLP classification (billing/HR/IT/policy/complaint) • Priority scoring (High / Medium / Low) • SLA category tagging • Confidence score per classification • Low-confidence flagging for human review | ✅ >90% classification accuracy ✅ Confidence score shown on every ticket ✅ Low-confidence emails flagged for review ✅ Tags applied within 10 seconds ✅ All tags written to ticketing system | Email body + subject → Claude API (structured JSON prompt) → return {type, priority, sla_bucket, confidence} → write tags to ticketing system | anthropic-claude-mcp, servicenow-mcp, freshdesk-mcp | High
E2 | Categorization & Tagging | E2-UJ2 | Sentiment Detection & Escalation Flagging | QA / Compliance, Team Lead | • Sentiment scoring (positive/neutral/negative/angry) • Real-time escalation flag for high-risk emails • Dashboard alert for negative sentiment • Sentiment trend over time | ✅ Negative sentiment flagged in real-time ✅ Escalation emails prioritized to top of queue ✅ Sentiment trend visible on dashboard ✅ Alert sent to Team Lead within 1 min | Claude API → sentiment analysis prompt → score stored in DB → trigger Slack alert if score < threshold | anthropic-claude-mcp, slack-mcp, postgres-mcp | High
E3 | Triage & Routing | E3-UJ1 | Smart Routing Engine | Inbox Analyst (L1), Automation Analyst | • Rule-based + AI hybrid routing • Routing to correct team/SME/queue • Fallback queue for unresolved routing • Routing audit log with decision reason • Manual override capability | ✅ 95%+ routing accuracy ✅ Misroutes < 5% ✅ Every routing decision logged with reason ✅ Manual override available to analyst ✅ Routing completes within 15 seconds | Classification output → match against routing rules matrix → assign in ticketing system → log decision reason → alert team | servicenow-mcp, jira-mcp, freshdesk-mcp, postgres-mcp | High
E4 | Response Management | E4-UJ1 | AI-Drafted Response Generation | Inbox Analyst, Senior Analyst | • Template-based draft generation • Personalized reply with customer name & context • Tone checker (professional, no casual language) • Compliance keyword filter • Analyst review + edit before send | ✅ Draft generated in < 5 seconds ✅ Tone is professional (no rude/casual language) ✅ HIPAA/GDPR sensitive terms masked ✅ Analyst can edit before send ✅ Sent email logged to CRM automatically | Retrieve email thread + customer history → Claude API (tone & compliance system prompt) → return draft → analyst approves/edits → send via email MCP | anthropic-claude-mcp, gmail-mcp, outlook-mcp, crm-mcp | High
E4 | Response Management | E4-UJ2 | Compliance Guardrails (HIPAA/GDPR/SOC 2) | QA / Compliance Officer | • PII detection before outbound send • Compliance flag + send block on violation • Audit log of all flagged items • QA dashboard with compliance rate • Sensitive data masking | ✅ PII detected 100% before outbound ✅ Blocked emails logged with reason ✅ QA dashboard shows compliance % ✅ Zero compliance violations in audit ✅ Alert sent to compliance officer on block | Pre-send hook → scan response body for PII patterns (regex + Claude) → if found, block + alert analyst → log to audit DB | anthropic-claude-mcp, postgres-mcp | Critical
E5 | SLA & Follow-up Management | E5-UJ1 | SLA Clock & Auto-Escalation | Team Lead, Senior Analyst | • SLA timer per email from time of receipt • Color-coded aging dashboard (Green/Yellow/Red) • Auto-alert at 80% SLA elapsed • Auto-escalation at 100% SLA breach • Slack + email notification on escalation | ✅ SLA timer starts at email receipt ✅ Alert fires at 80% elapsed ✅ Auto-escalation triggers at 100% ✅ SLA compliance % visible in dashboard ✅ All escalations logged | On email intake → store SLA deadline in DB → cron job checks every 5 min → trigger alert/escalation via Slack or email MCP | postgres-mcp, slack-mcp, gmail-mcp | High
E6 | Documentation & Audit Trail | E6-UJ1 | Auto-Logging to CRM / Ticketing System | Compliance Officer, QA Analyst | • Auto-log email + response + routing decision • Attachment archival • Searchable audit log by case ID / sender / date • Full history for audit readiness • Tamper-proof log entries | ✅ 100% emails logged ✅ Log includes timestamps, agent ID, action taken ✅ Searchable by case ID / sender / date range ✅ Attachments archived and linked to case ✅ Audit export available as PDF/Excel | Event-driven logging → every system action writes structured log to DB → CRM updated via API → attachment stored in filesystem | postgres-mcp, salesforce-mcp, hubspot-mcp, filesystem-mcp | High
E7 | Analytics & Continuous Improvement | E7-UJ1 | KPI Dashboard (Real-Time) | Team Lead, Ops Manager | • Volume metrics: emails received, processed, backlog • SLA metrics: FRT, SLA %, escalation rate • Quality: FCR, re-open rate, error rate, QA score • Customer: CSAT, complaint rate, sentiment trend • Automation: % auto-classified, % auto-responded, cost/email • Date range filters & export to Excel | ✅ Dashboard refreshes every 5 minutes ✅ All 6 KPI categories visible ✅ Date range filters work correctly ✅ Export to Excel/PDF available ✅ Role-based access (Team Lead vs Analyst view) | Aggregate data from DB → REST API → React dashboard → real-time polling every 5 min → export via Google Sheets MCP | postgres-mcp, google-sheets-mcp, slack-mcp | Medium
E7 | Analytics & Continuous Improvement | E7-UJ2 | Automation Opportunity Identification | Automation / Ops Analyst | • Identify repetitive query patterns • Recommend knowledge base updates • Template optimization suggestions • % manual effort reduction tracking • Cost per email trending | ✅ Top 10 repetitive query types surfaced weekly ✅ KB update recommendations generated automatically ✅ Template performance score visible ✅ Manual effort % tracked month-over-month ✅ Cost per email visible on dashboard | Aggregate classification data → Claude API (pattern analysis prompt) → generate recommendations report → post to Slack/email weekly | anthropic-claude-mcp, postgres-mcp, slack-mcp, google-sheets-mcp | Medium

## MCP Tools Map
MCP Tools — Master Reference Map
MCP Tool | Category | Purpose | Used In Epics | Notes
gmail-mcp | Email Integration | Ingest & send emails via Gmail | E1, E4 | OAuth 2.0 required
outlook-mcp | Email Integration | Ingest & send emails via Outlook/O365 | E1, E4 | Microsoft Graph API
zendesk-mcp | Ticketing | Ingest tickets from Zendesk inbox | E1 | Zendesk API key required
freshdesk-mcp | Ticketing | Tag, route, and update tickets in Freshdesk | E1, E2, E3 | Freshdesk API key required
servicenow-mcp | Ticketing / ITSM | Route and manage IT/HR tickets | E2, E3 | ServiceNow instance URL needed
jira-mcp | Project Management | Create and assign Jira issues for routed tickets | E3 | Jira Cloud or Server
anthropic-claude-mcp | AI / LLM | Classification, sentiment, response drafting, pattern analysis | E2, E4, E7 | Claude Sonnet recommended
postgres-mcp | Database | Store logs, SLA timers, audit trail, KPI data | E2, E3, E5, E6, E7 | Structured data backbone
slack-mcp | Notifications | Send real-time alerts for escalations, sentiment flags | E2, E5, E7 | Slack webhook or Bot token
crm-mcp | CRM | Fetch customer history for personalized responses | E4 | Salesforce / HubSpot
salesforce-mcp | CRM / Audit | Log interactions and audit trail to Salesforce | E6 | Salesforce connected app
hubspot-mcp | CRM / Audit | Alternative CRM for logging and audit | E6 | HubSpot API key
filesystem-mcp | Storage | Store and retrieve email attachments | E1, E6 | Local or cloud filesystem
google-sheets-mcp | Analytics / Export | Export KPI data and reports to Google Sheets | E7 | Google Service Account

## KPI Metrics Framework
Inbox Management — KPI & Metrics Framework
Category | KPI / Metric | Definition | Target / Benchmark | Frequency | Owner
Volume & Productivity | Emails Received / Day | Total inbound emails per day | Track baseline | Daily | Ops Manager
Volume & Productivity | Emails Processed / Agent | Emails handled per agent per day | >80/agent/day | Daily | Team Lead
Volume & Productivity | Average Handling Time (AHT) | Avg time to fully resolve one email | < 8 min | Daily | Team Lead
Volume & Productivity | Backlog Volume | Open unresolved emails at end of day | < 5% of daily volume | Daily | Team Lead
SLA & Timeliness | First Response Time (FRT) | Time from email receipt to first reply | < 2 hours | Real-time | Team Lead
SLA & Timeliness | SLA Compliance % | % emails resolved within SLA window | > 95% | Daily | Team Lead
SLA & Timeliness | Escalation Rate | % emails escalated beyond L1 | < 10% | Weekly | Team Lead
SLA & Timeliness | Aging of Open Emails | Emails open beyond SLA threshold | 0 breaches | Real-time | Team Lead
Quality | First Contact Resolution (FCR) | % queries resolved without follow-up | > 85% | Weekly | QA Analyst
Quality | Re-open Rate | % closed emails reopened by customer | < 5% | Weekly | QA Analyst
Quality | Error Rate | % wrong routing or wrong responses | < 2% | Weekly | QA Analyst
Quality | QA Score % | Quality audit score per agent/week | > 90% | Weekly | QA Analyst
Customer Experience | CSAT Score | Customer satisfaction post-resolution | > 4.0 / 5.0 | Monthly | Ops Manager
Customer Experience | Complaint Rate | % interactions resulting in a complaint | < 1% | Monthly | Ops Manager
Customer Experience | Negative Sentiment Trend | Trend of negative sentiment over time | Declining trend | Weekly | Team Lead
Compliance & Risk | HIPAA/GDPR Adherence | % emails with zero compliance violations | 100% | Daily | Compliance Officer
Compliance & Risk | Documentation Completeness | % cases with full audit trail | 100% | Weekly | Compliance Officer
Compliance & Risk | Audit Findings Count | Open audit findings from QA reviews | 0 critical | Monthly | Compliance Officer
Automation & Efficiency | % Auto-Classified Emails | Emails classified without human input | > 90% | Daily | Automation Analyst
Automation & Efficiency | % Auto-Responses Sent | Emails replied to without human draft | > 40% | Daily | Automation Analyst
Automation & Efficiency | Manual Effort Reduction | % reduction in manual handling vs baseline | > 30% | Monthly | Automation Analyst
Automation & Efficiency | Cost Per Email | Total ops cost divided by emails handled | Track & reduce | Monthly | Ops Manager

## Roles & Responsibilities
Inbox Management Team — Roles & Responsibilities
Role | Level | Key Responsibilities | Epics Involved | KPIs Owned | Tools Used
Inbox Analyst / Executive | L1 | • Email monitoring & intake • Basic categorization • Standard template responses • Ticket logging | E1, E2, E3, E4 | AHT, FRT, Emails Processed/Agent | Gmail, Outlook, Zendesk, Freshdesk
Senior Analyst | L2 | • Complex query handling • Escalation management • Personalized response drafting • L1 support & coaching | E3, E4, E5 | FCR, Re-open Rate, Escalation Rate | Claude AI Draft Tool, CRM, ServiceNow
Team Lead | Manager | • SLA management & monitoring • Workload balancing across team • Escalation decision-making • Daily KPI reviews | E5, E6, E7 | SLA Compliance %, Backlog, CSAT | SLA Dashboard, Slack Alerts, KPI Dashboard
QA / Compliance Analyst | Specialist | • Response quality audits • Compliance checks (HIPAA/GDPR) • Audit trail review • QA scoring | E4, E6 | QA Score %, Error Rate, Compliance % | Audit Log Tool, Postgres, Compliance Dashboard
Automation / Ops Analyst | Specialist | • AI classification tuning • Process optimization • Automation opportunity identification • Cost per email tracking | E2, E7 | % Auto-Classified, Manual Effort Reduction, Cost/Email | Claude MCP, Postgres, Analytics Dashboard
Ops Manager | Leadership | • Team performance oversight • Client SLA governance • Continuous improvement steering • Reporting to stakeholders | E5, E6, E7 | CSAT, SLA Compliance %, Cost Per Email | Executive Dashboard, Google Sheets Export