## User Story Backlog
📋 AI Inbox Management — User Story Backlog
Epic ID | Epic Name | Story ID | User Story | Business Objective | Acceptance Criteria | Priority | Sprint | Story Points | Status | % Complete
E1 | Inbox Monitoring & Intake | US-E1-01 | As an Inbox Analyst, I want all inbound emails auto-ingested from Gmail and Outlook so that no customer email is ever missed. | Ensure 100% email capture from all source systems within 30 seconds of receipt | ✅ Email ingested within 30 sec ✅ No email missed in 24hr window ✅ Metadata (sender, subject, timestamp) extracted ✅ Source system tagged on each record | High | Sprint 1 | 5 | Not Started | 0%
E1 | Inbox Monitoring & Intake | US-E1-02 | As an Inbox Analyst, I want an automatic acknowledgement sent to every customer so that they know their email was received. | Reduce customer anxiety and set expectation of response time via auto-ACK | ✅ Auto-ACK sent within 5 minutes ✅ Case reference number included ✅ ACK logged against the email record ✅ 100% coverage — no email skipped | High | Sprint 1 | 3 | Not Started | 0%
E2 | Categorization & Tagging | US-E2-01 | As an Inbox Analyst, I want every email automatically classified by type and priority so that I don't have to manually read and sort each one. | Eliminate manual triage effort and drive consistent, accurate routing through AI classification | ✅ >90% classification accuracy ✅ Confidence score on every email ✅ Low-confidence (<70%) flagged for human review ✅ Tags written to ticketing system within 10 sec | High | Sprint 2 | 8 | Not Started | 0%
E2 | Categorization & Tagging | US-E2-02 | As a Team Lead, I want negative or angry emails automatically flagged so that escalation-risk cases are prioritised before they escalate further. | Reduce escalations and protect CSAT by catching at-risk emails in real time | ✅ Sentiment scored on every email (positive/neutral/negative/angry) ✅ Negative sentiment flagged in real time ✅ Escalation-flagged emails jump to top of queue ✅ Slack alert sent to Team Lead within 1 min | High | Sprint 2 | 5 | Not Started | 0%
E3 | Triage & Routing | US-E3-01 | As an Inbox Analyst, I want every email automatically routed to the correct team or queue so that no email lands in the wrong place and time is not wasted. | Achieve 95%+ routing accuracy to reduce mis-routing, rework, and customer wait time | ✅ 95%+ routing accuracy ✅ Mis-routes < 5% ✅ Every routing decision logged with reason ✅ Manual override available to Team Lead ✅ Routing completes within 15 seconds | High | Sprint 3 | 8 | Not Started | 0%
E4 | Response Management | US-E4-01 | As an Inbox Analyst, I want AI to draft my email replies so that I only need to review and approve, not write from scratch. | Cut average handling time by 40% through AI-assisted response drafting | ✅ Draft generated in < 5 seconds ✅ Tone is professional (no casual language) ✅ Customer name and case ID included ✅ Analyst can edit before send ✅ Sent email logged to CRM automatically | High | Sprint 4 | 8 | Not Started | 0%
E4 | Response Management | US-E4-02 | As a Compliance Officer, I want every outbound email scanned for PII before it is sent so that we never violate HIPAA, GDPR, or SOC 2. | Achieve zero compliance violations in outbound communications | ✅ PII detected 100% before outbound send ✅ PII-containing emails blocked — hard stop ✅ Compliance violation logged immediately ✅ Compliance officer alerted on every block ✅ Zero compliance violations in audit | Critical | Sprint 4 | 5 | Not Started | 0%
E5 | SLA & Follow-up Management | US-E5-01 | As a Team Lead, I want every email tracked against its SLA deadline so that I can see what is at risk and take action before a breach occurs. | Achieve >95% SLA compliance by proactive alerting, not reactive firefighting | ✅ SLA timer starts at email receipt ✅ Alert fires at 80% of SLA elapsed ✅ Auto-escalation triggers at 100% (breach) ✅ SLA compliance % visible on dashboard ✅ All escalations logged with timestamp | High | Sprint 5 | 5 | Not Started | 0%
E6 | Documentation & Audit Trail | US-E6-01 | As a Compliance Officer, I want a complete, tamper-proof audit trail for every email interaction so that we are always audit-ready. | Ensure 100% audit completeness and zero compliance gaps for every email handled | ✅ 100% of emails logged — nothing missed ✅ Log includes timestamp, agent ID, action taken ✅ Attachments archived and linked to case ✅ Searchable by case ID / sender / date range ✅ Export available as PDF or Excel | High | Sprint 5 | 5 | Not Started | 0%
E7 | Analytics & Continuous Improvement | US-E7-01 | As an Ops Manager, I want a real-time KPI dashboard so that I can manage team performance and SLA health at a glance. | Give leadership instant visibility across all 6 KPI categories to drive data-driven decisions | ✅ Dashboard refreshes every 5 minutes ✅ All 6 KPI categories visible ✅ Date range filters work ✅ Export to Excel/PDF available ✅ Role-based view (Manager vs Analyst) | Medium | Sprint 6 | 8 | Not Started | 0%
E7 | Analytics & Continuous Improvement | US-E7-02 | As an Automation Analyst, I want the system to identify repetitive query patterns weekly so that I can automate them and reduce manual effort. | Reduce manual email handling by 30%+ through data-driven automation identification | ✅ Top 10 repetitive query types surfaced weekly ✅ KB update recommendations auto-generated ✅ Manual effort % tracked month-on-month ✅ Weekly report auto-posted to Slack | Medium | Sprint 6 | 5 | Not Started | 0%

## Sub-task Tracker
🔧 Sub-task Tracker — Daily Work Progress
ℹ️ Update Status & Completed Date to track progress. Story % Complete on Sheet 1 updates automatically.
S.No | Epic ID | Epic Name | Story ID | Sub-task ID | Summary | Priority | Status | Assignee | Blocked? | Dependencies | Sprint | Start Date | End Date | Completed Date | Days Left | Progress Notes | Comments
1 | E1 | Inbox Monitoring & Intake | US-E1-01 | ST-E1-01 | Connect Gmail via OAuth 2.0 and configure polling | High | Not Started | Sathishkumar | No |  | Sprint 1 |  |  |  | -
2 | E1 | Inbox Monitoring & Intake | US-E1-01 | ST-E1-02 | Connect Outlook via Microsoft Graph API | High | Not Started | Sathishkumar | No |  | Sprint 1 |  |  |  | -
3 | E1 | Inbox Monitoring & Intake | US-E1-01 | ST-E1-03 | Connect Zendesk & Freshdesk ticket ingestion | Medium | Not Started | Sathishkumar | No |  | Sprint 1 |  |  |  | -
4 | E1 | Inbox Monitoring & Intake | US-E1-01 | ST-E1-04 | Build email metadata extraction (sender, subject, body, timestamp) | High | Not Started | Sathishkumar | No |  | Sprint 1 |  |  |  | -
5 | E1 | Inbox Monitoring & Intake | US-E1-02 | ST-E1-05 | Build auto-ACK reply engine with case ID generator | High | Not Started | Sathishkumar | No |  | Sprint 1 |  |  |  | -
6 | E1 | Inbox Monitoring & Intake | US-E1-02 | ST-E1-06 | Store attachments via filesystem-mcp and link to case | Medium | Not Started | Sathishkumar | No |  | Sprint 1 |  |  |  | -
7 | E1 | Inbox Monitoring & Intake | US-E1-02 | ST-E1-07 | Write intake event to audit log (AG-06) | Medium | Not Started | Sathishkumar | No |  | Sprint 1 |  |  |  | -
8 | E2 | Categorization & Tagging | US-E2-01 | ST-E2-01 | Design classification taxonomy (billing/HR/IT/complaint/query/other) | High | Not Started | Sathishkumar | No |  | Sprint 2 |  |  |  | -
9 | E2 | Categorization & Tagging | US-E2-01 | ST-E2-02 | Build Claude API classification prompt with structured JSON output | High | Not Started | Sathishkumar | No |  | Sprint 2 |  |  |  | -
10 | E2 | Categorization & Tagging | US-E2-01 | ST-E2-03 | Implement confidence threshold logic and human-review queue | High | Not Started | Sathishkumar | No |  | Sprint 2 |  |  |  | -
11 | E2 | Categorization & Tagging | US-E2-01 | ST-E2-04 | Write classification tags to Freshdesk/ServiceNow via MCP | Medium | Not Started | Sathishkumar | No |  | Sprint 2 |  |  |  | -
12 | E2 | Categorization & Tagging | US-E2-01 | ST-E2-05 | Build fallback keyword classifier for LLM timeout scenarios | Medium | Not Started | Sathishkumar | No |  | Sprint 2 |  |  |  | -
13 | E2 | Categorization & Tagging | US-E2-02 | ST-E2-06 | Build Claude sentiment detection prompt (score -1.0 to +1.0) | High | Not Started | Sathishkumar | No |  | Sprint 2 |  |  |  | -
14 | E2 | Categorization & Tagging | US-E2-02 | ST-E2-07 | Implement escalation flag logic (score < -0.5 = flag) | High | Not Started | Sathishkumar | No |  | Sprint 2 |  |  |  | -
15 | E2 | Categorization & Tagging | US-E2-02 | ST-E2-08 | Trigger Slack alert to Team Lead on escalation flag | Medium | Not Started | Sathishkumar | No |  | Sprint 2 |  |  |  | -
16 | E2 | Categorization & Tagging | US-E2-02 | ST-E2-09 | Store sentiment score in postgres-mcp for dashboard | Medium | Not Started | Sathishkumar | No |  | Sprint 2 |  |  |  | -
17 | E3 | Triage & Routing | US-E3-01 | ST-E3-01 | Build routing rules matrix (billing→Finance, IT→IT Support, etc.) | High | Not Started | Sathishkumar | No |  | Sprint 3 |  |  |  | -
18 | E3 | Triage & Routing | US-E3-01 | ST-E3-02 | Implement Claude fallback routing for unmatched rule cases | High | Not Started | Sathishkumar | No |  | Sprint 3 |  |  |  | -
19 | E3 | Triage & Routing | US-E3-01 | ST-E3-03 | Assign ticket to correct team in ServiceNow / Jira via MCP | High | Not Started | Sathishkumar | No |  | Sprint 3 |  |  |  | -
20 | E3 | Triage & Routing | US-E3-01 | ST-E3-04 | Log routing decision + reason to postgres audit trail | Medium | Not Started | Sathishkumar | No |  | Sprint 3 |  |  |  | -
21 | E3 | Triage & Routing | US-E3-01 | ST-E3-05 | Build Team Lead manual override UI on dashboard | Low | Not Started | Sathishkumar | No |  | Sprint 3 |  |  |  | -
22 | E4 | Response Management | US-E4-01 | ST-E4-01 | Fetch customer history from CRM via crm-mcp for context | High | Not Started | Sathishkumar | No |  | Sprint 4 |  |  |  | -
23 | E4 | Response Management | US-E4-01 | ST-E4-02 | Build Claude response drafting prompt (tone + compliance rules) | High | Not Started | Sathishkumar | No |  | Sprint 4 |  |  |  | -
24 | E4 | Response Management | US-E4-01 | ST-E4-03 | Build human-in-loop analyst review & edit UI | High | Not Started | Sathishkumar | No |  | Sprint 4 |  |  |  | -
25 | E4 | Response Management | US-E4-01 | ST-E4-04 | Send approved email via gmail-mcp / outlook-mcp | High | Not Started | Sathishkumar | No |  | Sprint 4 |  |  |  | -
26 | E4 | Response Management | US-E4-01 | ST-E4-05 | Log sent email to CRM and audit trail | Medium | Not Started | Sathishkumar | No |  | Sprint 4 |  |  |  | -
27 | E4 | Response Management | US-E4-02 | ST-E4-06 | Build PII detection scanner (regex + Claude) for outbound emails | Critical | Not Started | Sathishkumar | No |  | Sprint 4 |  |  |  | -
28 | E4 | Response Management | US-E4-02 | ST-E4-07 | Implement hard-block on send when PII detected | Critical | Not Started | Sathishkumar | No |  | Sprint 4 |  |  |  | -
29 | E4 | Response Management | US-E4-02 | ST-E4-08 | Log compliance violation + alert compliance officer via Slack | High | Not Started | Sathishkumar | No |  | Sprint 4 |  |  |  | -
30 | E5 | SLA & Follow-up Management | US-E5-01 | ST-E5-01 | Store SLA deadline per email in postgres on intake | High | Not Started | Sathishkumar | No |  | Sprint 5 |  |  |  | -
31 | E5 | SLA & Follow-up Management | US-E5-01 | ST-E5-02 | Build cron job to check SLA status every 5 minutes | High | Not Started | Sathishkumar | No |  | Sprint 5 |  |  |  | -
32 | E5 | SLA & Follow-up Management | US-E5-01 | ST-E5-03 | Fire Slack + email alert at 80% SLA elapsed | High | Not Started | Sathishkumar | No |  | Sprint 5 |  |  |  | -
33 | E5 | SLA & Follow-up Management | US-E5-01 | ST-E5-04 | Auto-escalate to Team Lead queue at 100% breach | High | Not Started | Sathishkumar | No |  | Sprint 5 |  |  |  | -
34 | E5 | SLA & Follow-up Management | US-E5-01 | ST-E5-05 | Feed SLA data to real-time dashboard | Medium | Not Started | Sathishkumar | No |  | Sprint 5 |  |  |  | -
35 | E6 | Documentation & Audit Trail | US-E6-01 | ST-E6-01 | Build append-only event log schema in postgres-mcp | High | Not Started | Sathishkumar | No |  | Sprint 5 |  |  |  | -
36 | E6 | Documentation & Audit Trail | US-E6-01 | ST-E6-02 | Log every agent action as structured event (type, agent, email_id, timestamp) | High | Not Started | Sathishkumar | No |  | Sprint 5 |  |  |  | -
37 | E6 | Documentation & Audit Trail | US-E6-01 | ST-E6-03 | Sync interaction records to Salesforce / HubSpot via CRM MCP | Medium | Not Started | Sathishkumar | No |  | Sprint 5 |  |  |  | -
38 | E6 | Documentation & Audit Trail | US-E6-01 | ST-E6-04 | Archive attachments to filesystem-mcp with case linkage | Medium | Not Started | Sathishkumar | No |  | Sprint 5 |  |  |  | -
39 | E6 | Documentation & Audit Trail | US-E6-01 | ST-E6-05 | Build audit export to Excel/PDF functionality | Low | Not Started | Sathishkumar | No |  | Sprint 5 |  |  |  | -
40 | E7 | Analytics & Continuous Improvement | US-E7-01 | ST-E7-01 | Aggregate KPI data from postgres via SQL queries | High | Not Started | Sathishkumar | No |  | Sprint 6 |  |  |  | -
41 | E7 | Analytics & Continuous Improvement | US-E7-01 | ST-E7-02 | Build REST API to serve KPI data to dashboard | High | Not Started | Sathishkumar | No |  | Sprint 6 |  |  |  | -
42 | E7 | Analytics & Continuous Improvement | US-E7-01 | ST-E7-03 | Build React KPI dashboard with 5-min auto-refresh | High | Not Started | Sathishkumar | No |  | Sprint 6 |  |  |  | -
43 | E7 | Analytics & Continuous Improvement | US-E7-01 | ST-E7-04 | Implement date range filters and role-based access | Medium | Not Started | Sathishkumar | No |  | Sprint 6 |  |  |  | -
44 | E7 | Analytics & Continuous Improvement | US-E7-01 | ST-E7-05 | Add export to Google Sheets via google-sheets-mcp | Low | Not Started | Sathishkumar | No |  | Sprint 6 |  |  |  | -
45 | E7 | Analytics & Continuous Improvement | US-E7-02 | ST-E7-06 | Build Claude pattern-mining prompt over weekly classification data | High | Not Started | Sathishkumar | No |  | Sprint 6 |  |  |  | -
46 | E7 | Analytics & Continuous Improvement | US-E7-02 | ST-E7-07 | Generate structured automation opportunity report | Medium | Not Started | Sathishkumar | No |  | Sprint 6 |  |  |  | -
47 | E7 | Analytics & Continuous Improvement | US-E7-02 | ST-E7-08 | Auto-post weekly insight report to Slack channel | Medium | Not Started | Sathishkumar | No |  | Sprint 6 |  |  |  | -
Formulas:
Days Left = IF([Completed Date]<>"","✅ Done",IF([End Date]="","-",MAX(0,[End Date]-TODAY())))

## Sprint Dashboard
📊 Sprint Dashboard — Progress at a Glance
Sprint | Dates | Total Stories | Total Sub-tasks | Done | In Progress | Not Started | % Complete
Sprint 1 | 01 Apr – 14 Apr 2026 | 2 | 7 | 0 | 0 | 7 | 0%
Sprint 2 | 15 Apr – 28 Apr 2026 | 2 | 9 | 0 | 0 | 9 | 0%
Sprint 3 | 29 Apr – 12 May 2026 | 1 | 5 | 0 | 0 | 5 | 0%
Sprint 4 | 13 May – 26 May 2026 | 2 | 8 | 0 | 0 | 8 | 0%
Sprint 5 | 27 May – 09 Jun 2026 | 2 | 10 | 0 | 0 | 10 | 0%
Sprint 6 | 10 Jun – 23 Jun 2026 | 2 | 8 | 0 | 0 | 8 | 0%
📌 OVERALL PROJECT |  |  | 47 | 0 | 0 | 47 | 0%
📦 PROGRESS BY EPIC
Epic ID | Epic Name | Stories | Sub-tasks | Done | In Progress | Not Started | % Complete
E1 | Inbox Monitoring & Intake | 2 | 7 | 0 | 0 | 7 | 0%
E2 | Categorization & Tagging | 2 | 9 | 0 | 0 | 9 | 0%
E3 | Triage & Routing | 1 | 5 | 0 | 0 | 5 | 0%
E4 | Response Management | 2 | 8 | 0 | 0 | 8 | 0%
E5 | SLA & Follow-up Management | 1 | 5 | 0 | 0 | 5 | 0%
E6 | Documentation & Audit Trail | 1 | 5 | 0 | 0 | 5 | 0%
E7 | Analytics & Continuous Improvement | 2 | 8 | 0 | 0 | 8 | 0%

## MCP Tools Map
MCP Tools — Master Reference Map
MCP Tool | Category | Purpose | Used In Epics | Notes
gmail-mcp | Email Integration | Ingest & send emails via Gmail | E1, E4 | OAuth 2.0 required
outlook-mcp | Email Integration | Ingest & send emails via Outlook/O365 | E1, E4 | Microsoft Graph API
zendesk-mcp | Ticketing | Ingest tickets from Zendesk inbox | E1 | Zendesk API key required
freshdesk-mcp | Ticketing | Tag, route, and update tickets in Freshdesk | E1, E2, E3 | Freshdesk API key required
servicenow-mcp | Ticketing / ITSM | Route and manage IT/HR tickets | E2, E3 | ServiceNow instance URL needed
jira-mcp | Project Management | Create and assign Jira issues for routed tickets | E3 | Jira Cloud or Server
anthropic-claude-mcp | AI / LLM | Classification, sentiment, response drafting, pattern analysis | E2, E4, E7 | Claude Sonnet recommended
postgres-mcp | Database | Store logs, SLA timers, audit trail, KPI data | E2, E3, E5, E6, E7 | Structured data backbone
slack-mcp | Notifications | Send real-time alerts for escalations, sentiment flags | E2, E5, E7 | Slack webhook or Bot token
crm-mcp | CRM | Fetch customer history for personalized responses | E4 | Salesforce / HubSpot
salesforce-mcp | CRM / Audit | Log interactions and audit trail to Salesforce | E6 | Salesforce connected app
hubspot-mcp | CRM / Audit | Alternative CRM for logging and audit | E6 | HubSpot API key
filesystem-mcp | Storage | Store and retrieve email attachments | E1, E6 | Local or cloud filesystem
google-sheets-mcp | Analytics / Export | Export KPI data and reports to Google Sheets | E7 | Google Service Account

## KPI Metrics Framework
Inbox Management — KPI & Metrics Framework
Category | KPI / Metric | Definition | Target / Benchmark | Frequency | Owner
Volume & Productivity | Emails Received / Day | Total inbound emails per day | Track baseline | Daily | Ops Manager
Volume & Productivity | Emails Processed / Agent | Emails handled per agent per day | >80/agent/day | Daily | Team Lead
Volume & Productivity | Average Handling Time (AHT) | Avg time to fully resolve one email | < 8 min | Daily | Team Lead
Volume & Productivity | Backlog Volume | Open unresolved emails at end of day | < 5% of daily volume | Daily | Team Lead
SLA & Timeliness | First Response Time (FRT) | Time from email receipt to first reply | < 2 hours | Real-time | Team Lead
SLA & Timeliness | SLA Compliance % | % emails resolved within SLA window | > 95% | Daily | Team Lead
SLA & Timeliness | Escalation Rate | % emails escalated beyond L1 | < 10% | Weekly | Team Lead
SLA & Timeliness | Aging of Open Emails | Emails open beyond SLA threshold | 0 breaches | Real-time | Team Lead
Quality | First Contact Resolution (FCR) | % queries resolved without follow-up | > 85% | Weekly | QA Analyst
Quality | Re-open Rate | % closed emails reopened by customer | < 5% | Weekly | QA Analyst
Quality | Error Rate | % wrong routing or wrong responses | < 2% | Weekly | QA Analyst
Quality | QA Score % | Quality audit score per agent/week | > 90% | Weekly | QA Analyst
Customer Experience | CSAT Score | Customer satisfaction post-resolution | > 4.0 / 5.0 | Monthly | Ops Manager
Customer Experience | Complaint Rate | % interactions resulting in a complaint | < 1% | Monthly | Ops Manager
Customer Experience | Negative Sentiment Trend | Trend of negative sentiment over time | Declining trend | Weekly | Team Lead
Compliance & Risk | HIPAA/GDPR Adherence | % emails with zero compliance violations | 100% | Daily | Compliance Officer
Compliance & Risk | Documentation Completeness | % cases with full audit trail | 100% | Weekly | Compliance Officer
Compliance & Risk | Audit Findings Count | Open audit findings from QA reviews | 0 critical | Monthly | Compliance Officer
Automation & Efficiency | % Auto-Classified Emails | Emails classified without human input | > 90% | Daily | Automation Analyst
Automation & Efficiency | % Auto-Responses Sent | Emails replied to without human draft | > 40% | Daily | Automation Analyst
Automation & Efficiency | Manual Effort Reduction | % reduction in manual handling vs baseline | > 30% | Monthly | Automation Analyst
Automation & Efficiency | Cost Per Email | Total ops cost divided by emails handled | Track & reduce | Monthly | Ops Manager

## Roles & Responsibilities
Inbox Management Team — Roles & Responsibilities
Role | Level | Key Responsibilities | Epics Involved | KPIs Owned | Tools Used
Inbox Analyst / Executive | L1 | • Email monitoring & intake • Basic categorization • Standard template responses • Ticket logging | E1, E2, E3, E4 | AHT, FRT, Emails Processed/Agent | Gmail, Outlook, Zendesk, Freshdesk
Senior Analyst | L2 | • Complex query handling • Escalation management • Personalized response drafting • L1 support & coaching | E3, E4, E5 | FCR, Re-open Rate, Escalation Rate | Claude AI Draft Tool, CRM, ServiceNow
Team Lead | Manager | • SLA management & monitoring • Workload balancing across team • Escalation decision-making • Daily KPI reviews | E5, E6, E7 | SLA Compliance %, Backlog, CSAT | SLA Dashboard, Slack Alerts, KPI Dashboard
QA / Compliance Analyst | Specialist | • Response quality audits • Compliance checks (HIPAA/GDPR) • Audit trail review • QA scoring | E4, E6 | QA Score %, Error Rate, Compliance % | Audit Log Tool, Postgres, Compliance Dashboard
Automation / Ops Analyst | Specialist | • AI classification tuning • Process optimization • Automation opportunity identification • Cost per email tracking | E2, E7 | % Auto-Classified, Manual Effort Reduction, Cost/Email | Claude MCP, Postgres, Analytics Dashboard
Ops Manager | Leadership | • Team performance oversight • Client SLA governance • Continuous improvement steering • Reporting to stakeholders | E5, E6, E7 | CSAT, SLA Compliance %, Cost Per Email | Executive Dashboard, Google Sheets Export