## Project Tracker
📋 Personal Project Tracker — Sprint & Story Management
ℹ️ Use dropdown menus in Priority, Status & Blocked columns ¦ Dates: DD-MM-YYYY ¦ Colour coding: 🟢 Done 🟡 In Progress 🔴 Blocked ⚪ Not Started
S.No | Project | Sprint | Sprint Start | Sprint End | Epic | Story ID | Story | Business Objective | Acceptance Criteria | Sub-task ID | Summary | Priority | Status | Assignee | Blocked | Dependencies | Start Date | End Date | Completed Date | Days Left | Comments
1 | Inbox Mgmt AI | Sprint 1 | 01-04-2026 | 14-04-2026 | E1 - Inbox Monitoring | US-001 | As an Inbox Analyst, I want all emails auto-ingested so nothing is missed | Ensure 100% email capture from all sources within 30 seconds | ✅ Email ingested <30s ✅ Auto-ACK sent <5min ✅ Attachments stored | ST-001 | Connect Gmail via OAuth & poll inbox | High | In Progress | Sathishkumar | No | - | 01-04-2026 | 07-04-2026 |  |  | Gmail credentials ready
2 | Inbox Mgmt AI | Sprint 1 | 01-04-2026 | 14-04-2026 | E1 - Inbox Monitoring | US-001 | As an Inbox Analyst, I want all emails auto-ingested so nothing is missed | Ensure 100% email capture from all sources within 30 seconds | ✅ Email ingested <30s ✅ Auto-ACK sent <5min ✅ Attachments stored | ST-002 | Connect Outlook via Microsoft Graph API | High | Not Started | Sathishkumar | No | ST-001 | 08-04-2026 | 12-04-2026
3 | Inbox Mgmt AI | Sprint 1 | 01-04-2026 | 14-04-2026 | E1 - Inbox Monitoring | US-002 | As an Analyst, I want auto-ACK emails sent so customers know we received their request | Auto-ACK sent within 5 min with case reference number | ✅ ACK sent <5min ✅ Case ID in subject ✅ 100% coverage | ST-003 | Build auto-ACK reply engine with case ID generator | High | Not Started | Sathishkumar | Yes | ST-001, ST-002 | 10-04-2026 | 14-04-2026 |  |  | Blocked on email connections
4 | Inbox Mgmt AI | Sprint 2 | 15-04-2026 | 28-04-2026 | E2 - Classification | US-003 | As an Analyst, I want emails auto-classified by Claude AI so I don't read each one manually | Achieve >90% classification accuracy with confidence scores | ✅ >90% accuracy ✅ Confidence score shown ✅ Low-confidence flagged | ST-004 | Integrate Claude API for email classification | High | Not Started | Sathishkumar | No | ST-001 | 15-04-2026 | 20-04-2026 |  |  | Use claude-sonnet model
5 | Inbox Mgmt AI | Sprint 2 | 15-04-2026 | 28-04-2026 | E2 - Classification | US-003 | As an Analyst, I want emails auto-classified by Claude AI so I don't read each one manually | Achieve >90% classification accuracy with confidence scores | ✅ >90% accuracy ✅ Confidence score shown ✅ Low-confidence flagged | ST-005 | Build sentiment detection & escalation flag | Medium | Not Started | Sathishkumar | No | ST-004 | 21-04-2026 | 25-04-2026 |  |  | Run in parallel with classification
6 | Inbox Mgmt AI | Sprint 3 | 29-04-2026 | 12-05-2026 | E3 - Routing | US-004 | As a Team Lead, I want smart routing so every email reaches the right team instantly | 95%+ routing accuracy with full decision audit log | ✅ 95%+ accuracy ✅ Every decision logged ✅ Override available | ST-006 | Build routing rules matrix (billing/HR/IT/CS) | High | Not Started | Sathishkumar | No | ST-004 | 29-04-2026 | 05-05-2026 |  |  | Rules doc needed from client
7 | Inbox Mgmt AI | Sprint 3 | 29-04-2026 | 12-05-2026 | E4 - Response | US-005 | As an Analyst, I want AI-drafted responses so I only review, not write from scratch | Draft generated <5 sec, PII masked, tone professional | ✅ Draft <5sec ✅ PII 100% masked ✅ Human approval step | ST-007 | Build Claude response draft generation with tone check | High | Not Started | Sathishkumar | No | ST-006 | 06-05-2026 | 12-05-2026
Formulas:
Days Left = IF([Completed Date]<>"","Done",IF([End Date]="","-",MAX(0,DATEVALUE(TEXT([End Date],"DD-MM-YYYY"))-TODAY())))

## Legend & Guide
📖 Legend & User Guide — Project Tracker
STATUS COLOURS
Done | Story/task fully completed
In Progress | Actively being worked on
In Review | Under peer / QA review
On Hold | Paused — waiting for input
Not Started | Not yet begun
Cancelled | Dropped from scope
PRIORITY COLOURS
Critical | Must fix immediately — blocks everything
High | Important — complete this sprint
Medium | Should complete — next in queue
Low | Nice to have — if bandwidth allows
BLOCKED COLOURS
Yes | Task is blocked — add dependency in Dependencies column
No | Task is not blocked
COLUMN GUIDE
S.No | Auto-incrementing row number
Project | Name of the project this work belongs to
Sprint | Sprint name or number (e.g. Sprint 1)
Sprint Start/End | Sprint boundaries — format DD-MM-YYYY
Epic | High-level feature group (e.g. E1 - Inbox Monitoring)
Story ID | Unique ID for the user story (e.g. US-001)
Story | Full user story text — As a [who], I want [what] so that [why]
Business Objective | What business goal this story achieves
Acceptance Criteria | Conditions that must be true for this story to be 'Done'
Sub-task ID | Unique ID for the individual sub-task (e.g. ST-001)
Summary | Short description of the sub-task work
Priority | Critical / High / Medium / Low — use dropdown
Status | Current state of the task — use dropdown
Assignee | Person responsible for this sub-task
Blocked | Yes/No — use dropdown. If Yes, fill Dependencies
Dependencies | Sub-task IDs or descriptions that must be done first
Start Date | When work on this sub-task begins (DD-MM-YYYY)
End Date | Target completion date (DD-MM-YYYY)
Completed Date | Actual date task was finished (DD-MM-YYYY)
Days Left | Auto-calculated: days until End Date (shows 'Done' when completed)
Comments | Free text — blockers, notes, links, decisions